## Blatt1
Number | Story | Estimation | Sprint 0 | 1
1 | Consistent Page Frame | 5 | Sprint 1 | 4
2 | Signup | 2 |  | 3
3 | User Interface Language Selection | 2 |  | 5
4 | Advertisment of the 3 big sections | 2 |  | 6
5 | Introduction | 1 |  | 2
6 | Live Feed | 1 |  | 28
7 | Featured Content | 2 | Sprint 2 | 10
8 | Projects Widget on the Start Page | 3 |  | 34
9 | Create Content as a Visitor | 3 |  | 11
10 | User Menu | 1 |  | 14
11 | Main Page - Personal Overview | 13 |  | 20
12 | Groups | 8 |  | 15
13 | Projects | 3 |  | 12
14 | Create new Content | 3 | Sprint 3 | 11
15 | Create new Groups | 2 |  | 18
16 | Create new Projects | 2 |  | 40
17 | Requesting More Human Resources for Projects | 5 |  | 19
18 | Sidebars and Menus | 2
19 | Search | 8
20 | Content Detail Page | 2
21 | Rating | 100
22 | Profile Settings | 2
25 | Global Administration | 13
27 | Categories | 1
28 | Login & Password Recovery | 2
29 | Invite People to Groups | 3
30 | Invite People to Projects | 5
31 | Spin Off Projects | 8
32 | Removing Group Members | 3
33 | Removing Project Members | 2
34 | Main Navigation | 3
35 | Merge accounts with same email | 5
36 | Registration form validation | 1
37 | Translation roundup | 8
38 | Captcha reload | 2
39 | Privacy settings | 2
40 | Streamlined content properties | 20
41 | Matching articles | 5
42 | Matching users | 5
43 | Matching groups | 8
44 | Matching projects | 8
45 | User profile page | 2